## Registry
Ref: | Description of risk | Likelihood | Seriousness | Grade | Actions | Responsible officer
1 | Not enough time to finish tasks / milestones listed in Gantt Chart | M | E | A | Work on weekends | Team
2 | Documents get lost | L | E | A | Store all documents on Google Drive. If someone deletes a file, recover from bin. | Team
3 | Team member(s) not sharing fair taskload | M | L | D | Mandatory team discussion and consequential iPeer evaluations. | Team
4 | Absence of team member(s) from meetings | L | M | D | Mandatory team discussion and consequential iPeer evaluations. | Team
5 | Realizing major section(s) are missing in report | M | E | A | Ensure there is a detailed checklist of report requirements. Have each team member initial items completed. | Team

## Index
Rating for likelihood and seriousness for each risk
L | Rated as low | E | Rated as extreme (used for seriousness only)
M | Rated as medium | NA | Not assessed
H | Rated as high
Grade: Combined effect of likelihood/seriousness
Seriousness
Likelihood |  | low | medium | high | EXTREME
| low | E | D | C | A
| medium | D | C | B | A
| high | C | B | A | A
Recommended actions for grades of risk
Grade | Risk actions
A | Actions to reduce the likelihood and seriousness to be identified and implemented as soon as the project commences.
B | Actions to reduce the likelihood and seriousness to be identified and appropriate actions implemented during project execution.
C | Actions to reduce the likelihood and seriousness to be identified and costed for possible action if funds permit.
D | To be noted - no action is needed unless grading increases over time.
E | To be noted - no action is needed unless grading increases over time.
Change to grade since last assessment
NEW | New risk | ¯ | Grading decreased
— | No change to grade | ­ | Grading increased